## Slide 1
PROFESSIONAL SERVICES · MONTHLY EXECUTIVE SYNTHESIS
Portfolio Health Review
S2P Implementation Programs — Titan (Outokumpu) & UniSan
July 2026
Generated automatically by the Project Health Reporting Agent · Deterministic scoring, LLM-assisted narrative

## Slide 2
PORTFOLIO AT A GLANCE
Both programs read Red today — for very different reasons
Professional Services Portfolio Health Review · July 2026
2
TITAN — Outokumpu
RED
Titan S2P Implementation
PM: Aftab Hashambhai · Active phase: Configuration and Build phase
44.6
composite score / 100
71%
complete
62.6%
tasks slipped
Why this status:
11 critical-path task(s) have slipped their baseline. 3 task(s) are On Hold: Supplier Notification template, OTK to share D&B creds, Enable D & B App.
UNISAN
RED
UniSan S2P Implementation
PM: Rajat Bothra · Active phase: Training Phase I
91.2
composite score / 100
44%
complete
0.8%
tasks slipped
Why this status:
4 phase(s) are Red, including possibly the active phase.

## Slide 3
TREND ACROSS PROJECTS
Schedule drift is compounding on Titan — and acute, not chronic, on UniSan
Professional Services Portfolio Health Review · July 2026
3
Chart: Cumulative average schedule variance (days)
| 12-05 | 02-03 | 02-20 | 03-20 | 03-26 | 04-03 | 04-09 | 05-19 | 06-16 | 06-26
Titan (Outokumpu) | 0 | 0 | 0.6 | -0.6 | -2.7 | -4.6 | -5.8 | -5.3 | -5.7 | -5.8
UniSan | 0 | 0.9 | 1.9 | 1.3 | 1.1 | 0.9 | 0.9 | 1 | 0.8 | 0.9
TITAN
Delays are compounding: mean variance moved from on-time to −11.2 days and is still trending down, not flattening. Float is being consumed faster than it's recovered.
UNISAN
Aggregate schedule is healthy (+1.2 days, 0.8% of tasks slipped) — but the currently active phase, Training Phase I, is itself Red. This is a live blocker, not historical drag.

## Slide 4
CROSS-PROJECT THEME
Resourcing concentration is a bus-factor risk on Titan
Professional Services Portfolio Health Review · July 2026
4
Chart: Owner concentration (% of tasks held by busiest owner)
| Titan | UniSan
Busiest owner's share of tasks | 66.7 | 19.1
2
distinct owners on Titan
vs. 26 on UniSan
66.7%
of Titan's tasks sit with one owner
vs. 19.1% on UniSan
Recommendation
Cross-train a second owner onto Titan's critical-path tasks now, before the busiest owner becomes a single point of failure during the remaining Configuration & Build work.

## Slide 5
CROSS-PROJECT THEME
Blockers cluster on the client side — and reporting habits diverge by PM
Professional Services Portfolio Health Review · July 2026
5
Client-side dependencies are the dominant blocker type
Titan currently has 3 tasks On Hold, and all trace back to items waiting on the client rather than on Zycus-side effort:
Supplier Notification template
OTK to share D&B creds
Enable D & B App
UniSan currently has none on hold — but its low task-level detail (no status comments logged) means emerging client-side blockers there may simply be under-reported rather than absent.
Reporting discipline varies by PM — and it shows in the data
Chart: 
| Titan (Aftab) | UniSan (Rajat)
Logged status comments | 16 | 0
Sentiment and blocker-context signals are only computable where PMs log commentary. Standardizing this is the single highest-leverage data fix for next cycle's reporting.

## Slide 6
EMERGING RISKS & RECOMMENDATIONS
Three portfolio-level actions for this cycle
Professional Services Portfolio Health Review · July 2026
6
Standardize weekly status-comment logging
Make it a required field across all project plans. Sentiment and blocker-context signals are currently unavailable on UniSan for exactly this reason.
Add a Budget Burn column to the plan template
No project in the portfolio currently tracks cost data, so today's RAG is schedule-and-execution-only. This is the fastest way to close that gap next cycle.
Introduce a client-readiness checklist at kickoff
Credentials, sample data, and named approvers — captured up front — would pull Titan's current on-hold items earlier, before they sit on the critical path.

## Slide 7
Full transparency, on request
Every status on this deck traces back to a reproducible reasoning trail — the same signals, weights, and overrides defined in the RAG methodology, run against each project's live plan.
One-page RAG methodology
Weekly reports per project, with full reasoning
Working agent — code, tests, and run instructions
Next monthly review: early August 2026 · Weekly reports run automatically every Monday