Project Health RAG Methodology

Professional Services Project Health Reporting Agent  ·  Phase 1 Framework Definition

Purpose

Give leadership a Red/Amber/Green read on every project that is computed the same way every time, explained in plain English, and safe to trust even when the underlying data is incomplete or inconsistent between project managers.

Signals and Weights

| Signal | Wt. | What it measures | Data source |
| --- | --- | --- | --- |
| Schedule slippage | 35% | % of tasks behind their baseline finish date, average and worst-case slip in days | Baseline vs. actual Finish; Variance column |
| Milestone health | 25% | Share of phases currently Red/Amber; tasks Not Started past their baseline start | Phase/Milestone rollups, task Status |
| Blockers | 25% | On-Hold tasks, stalled in-progress tasks, At-Risk flags, negative float on critical tasks | On Hold?, At Risk?, Total Float, Critical? flags |
| Stakeholder sentiment | 10% | Lexical tone of free-text PM commentary (negative vs. positive keyword balance) | Status Comment / Comments free text |
| Critical path | 5% | Share of Critical-flagged tasks that have slipped their baseline | Critical? flag + Variance |

Score → Status, then Hard Overrides

Weighted scores combine into a single 0–100 composite: ≥ 80 → Green   ·   60–79 → Amber   ·   < 60 → Red.

Three override rules can only move the status down, never up — because a healthy-looking average can hide one acute, specific problem:

- Any Critical-path task with negative schedule variance → capped at Amber.

- Any unresolved On-Hold / blocked task → capped at Amber.

- The active phase itself is Red (not just a past phase) → forced to Red.

Assumptions

- Budget/cost burn is not scored — neither sample plan contains cost data. The signal is a placeholder in the config, ready the moment a plan carries a Budget column, rather than being estimated from nothing.

- Sentiment is a keyword-based lexical scan of free-text PM comments, not a validated survey — its influence on the score is capped and it is labeled low-confidence in every report.

- Where a plan lacks a task-level RAG column, Schedule Health is used as a proxy; where a plan lacks a Level column, Ancestors depth is used for hierarchy. Both substitutions are logged as data-quality notes, never applied silently.

- A Data Confidence score (0–100) accompanies every RAG status, penalizing missing required fields, so "Red with complete data" and "Red with major data gaps" are never presented identically.